Material Delays

Triggers:

- Delivery date slips

- Long-lead items not ordered in time

- Supply chain disruption (e.g., port delays, customs issues)

Signals:

- Open purchase orders past due

- Lead times exceeding schedule buffers

- Repeated supplier change requests

Actions:

- Verify order status with suppliers and logistics teams — get updated ETAs

- Source alternate materials or vendors (pre-vetted if possible)

- Re-sequence work to prioritize areas not dependent on delayed materials

- Communicate delay to stakeholders with updated timelines

Product:

- Auto-alert when material ETAs exceed threshold

- Suggested alternate vendors from marketplace API

- Re-sequencing tool to visualize schedule impact

Labor Shortages

Triggers:

- Crew no-shows

- Trade-specific labor unavailable in region

- Health/safety protocols reducing workforce

Signals:

- Lower-than-expected crew headcount

- Subcontractor delay notices

- High trade demand in surrounding projects/regions

Actions:

- Engage backup labor sources

- Adjust sequence or scope to work around impacted trades

- Offer overtime or shift adjustments if feasible

- Pull in tasks from future phases (if they don’t require same labor pool)

- Track and log delay for reporting/dispute defense

Product:

- Labor availability heatmap (by trade, region)

- Notifications when crew counts fall below thresholds

- Suggested task reshuffle based on available labor

Subcontractor Underperformance

Triggers:

- Missed milestones

- Poor workmanship

- Repeated safety incidents or inspection failures

Signals:

- Schedule slippage from one trade

- Increase in rework/change orders

- Unclosed punch items piling up

Actions:

- Initiate performance review or site walk with subcontractor PM

- Issue corrective action plan with specific milestones

- Deploy QC/safety audit team for documentation and oversight

- Withhold payment/backcharge as needed per contract

- Use backup subcontractor, if risk escalates

Product:

- Subcontractor risk score dashboard

- Alert when subs trigger performance thresholds (e.g., missed 2 milestones)

- Auto-suggest prequalified backup contractors

Weather

Triggers:

- Rain, snow, wind, extreme temperatures

- Site flooding, material damage

Signals:

- Forecasts for severe weather events

- Delays in concrete curing, roofing, excavation

- Work paused due to unsafe conditions

Actions:

- Shift to indoor work or trades not impacted

- Re-schedule weather-sensitive tasks

- Cover/protect materials and equipment

- Extend buffers for affected tasks

- Log weather conditions for force majeure or insurance claims

Product:

- Weather API integration with predictive impact by task type

- Alerts when forecasts exceed risk thresholds

- Auto-generated documentation logs

Observations / Change Orders

Triggers:

- Client-driven changes (design preferences, scope creep)

- RFIs leading to scope revisions

- Code compliance adjustments mid-project

Signals:

- Spike in RFIs or design clarifications

- Change orders not approved or priced promptly

- High volume of field observations

Actions:

- Quantify schedule & cost impact of change

- Formalize change order through contract vehicle

- Update schedule & re-sequence trades

- Escalate to Owner/PM If decisions lag

- Track delay for potential claims/delay damages

Product:

- RFI/change order volume tracker

- Delay calculator based on scope additions

- Pre-built “impact memo” generator to share with owners or execs

Example

Delay Risk Detected: Material Delay

Trigger: Steel delivery for level 2 framing is 7 days late

Impact: Critical task starting 4/29 will slip 3–5 days

Suggested Actions:

Contact supplier to get updated ETA

Source from alternate vendor

Re-sequence task: shift to HVAC rough-in in Zone A

Notify Owner/GC of projected delay